## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_DemoCart_1.0
Project Name | DemoCart_1.0
Prepared/Modified by | Role | Date of Preparation
Rustic Blooms | Test Engineer | 2018-03-08
Reviewed by | Role | Date of Review
Test Lead
Approved by | Role | Date of Approval
Test Manager
Circulation List
Version Number | 1

## Defect Tracking Sheet
Project ID: | PRJ_BankingExamPortal_2.1 | [23 empty] | VERIFIED
Project Name: | Banking Exam Portal_2.1
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments | REOPENED | Coding | Internal Dev
DF_DEMOCART_01 | CHECKOUT | The Checkout button is not working when clicked on it. | Detailed Description: The Checkout button is not working when clicked on it. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. The application does not proceed further. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_003
DF_DEMOCART_02 | QUANTITY | The Quantity field is accepting special characters. | Detailed Description: The Quantity field is accepting special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required alongwith some special characters. 7. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity with some special characters. The application accepts the quantity and does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_003
DF_DEMOCART_03 | QUANTITY | The Quantity field is accepting alphabets. | Detailed Description: The Quantity field is accepting alphabets. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required alongwith alphabets. 7. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity with alphabets. The application accepts the quantity and does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_003
DF_DEMOCART_04 | REVIEW | The review field is accepting special characters. | Detailed Description: The review field is accepting special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity 7. Enter the review with alphanumeric values 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity and reviews. Enter special characters in the reviews. The application accepts the reviews and does not proceed further. | Coding | Internet Explorer | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_003
DF_DEMOCART_05 | REVIEW | The review field is accepting aplhanumeric values and numbers. | Detailed Description: The review field is accepting aplhanumeric values and numbers. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required. 7. Enter the review with alphanumeric values. 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity and review with alphanumeric values. The application accepts the reviews and does not proceed further. | Coding | Internet Explorer | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_003
DF_DEMOCART_06 | SHOPPING CART | The coupon code field does not accept any values. | Detailed Description: The coupon code field does not accept any values. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required. 7. Enter a coupon code 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity and coupon code. The application does not accept the coupon code and does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_004
DF_DEMOCART_07 | SHOPPING CART | The gift certificate field does notr accept any values. | Detailed Description: The gift certificate field does notr accept any values. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required. 7. Enter a gift certificate 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity and gift certificate. The application does not accept the gift certificate and does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.1 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_004
DF_DEMOCART_08 | SHOPPING CART | The post code field of Estimate Shipping & Taxes section accepts alphabets. | Detailed Description: The post code field of Estimate Shipping & Taxes section accepts alphabets. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required. 7. Enter the shipping address. 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity. Enter shipping address. The application does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.1 | 2018-03-08 | Rustic Blooms |  | ACT | Test Cycle 1 | TC_Reg_004
DF_DEMOCART_09 | SHOPPING CART | The post code field of Estimate Shipping & Taxes section accepts special characters. | Detailed Description: The post code field of Estimate Shipping & Taxes section accepts special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required. 7. Enter the shipping address. 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity. Enter shipping address. The application does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 2.1 | Build 1.2 | 2018-03-09 | Rustic Blooms |  | ACT | Test Cycle 2 | TC_Reg_005
DF_DEMOCART_10 | SHOPPING CART | The post code field of Estimate Shipping & Taxes section accepts alphanumeric values. | Detailed Description: The post code field of Estimate Shipping & Taxes section accepts alphanumeric values. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Add an item to the cart 6. Enter the quantity required. 7. Enter the shipping address. 8. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. The application proceeds to the next page and we add an item to the cart. Enter the quantity. Enter shipping address. The application does not proceed further. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 3.1 | Build 1.3 | 2018-03-10 | Rustic Blooms |  | ACT | Test Cycle 3 | TC_Reg_006
DF_DEMOCART_11 | DESKTOPS | "Show All Desktops" diaplays all the products hosted by the website. | Detailed Description: "Show All Desktops" diaplays all the products hosted by the website. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Enter valid username and password 5. Click on "Show All Desktops" 6. Add an item to cart 7. Click on Checkout button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid login details. Click on "Show All Desktops". Add an item to the cart. Click on checkout. The applicatoin does not proceed further. | Coding | Internet Explorer | Internal Dev | High | High | 4.1 | Build 1.4 | 2018-03-11 | Rustic Blooms |  | ACT | Test Cycle 4 | TC_Reg_007